## Week 1+2
PROJECT REPORT
Group | Group 2
Week 1,2 | Iteration 0(06/09/2021-17/09/2021)
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Select, study & analyze assignments | Completed
2 | Create Git environment | Completed
3 | Create database | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Create Git environment | Nghia
2 | Select, study & analyze assignments | All member
3 | Database | All member
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Sử dụng Gitlab
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Update database | 26/09/2021
2 | code | 26/09/2021 | Login,logout, Register, change password, home page(employee, employer,admin), view profile, edit profile, notification,
3 | debug | 26/09/2021
4 | test | 26/09/2021
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## Week 3+4
PROJECT REPORT
Group | Group 2
Week 3+4 | Iteration 2 (20/09/2021-03/10/2021)
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | User Authorization | Completed
2 | Log In | Completed
3 | Register | Completed
4 | Change Password | Completed
5 | Home Page( for employee, employer, admin) | Completed
6 | Edit Profile | Completed
7 | View Profile | Completed
8 | Log Out | Completed
9 | Debug | In Progress
10 | Test | In Progress
11 | Update Database | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | User Authorization | Nghia
2 | Log In | Kien
3 | Register | Loc
4 | Log out | Loc
5 | Change Password | Nghia
6 | Home Page( for employee, employer, admin) | Loc,Nghia,Kien
8 | Edit Profile | Nghia
9 | View Profile | Kien
10 | Debug | all member
11 | Test | all member
12 | Update Database | all member
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Do chỉnh sửa frontend nên backend bị 1 số lỗi | Completed
2 | Code convention | Completed | Sửa các code convention theo yêu cầu của giáo viên
3 | Fix Bug | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Code | 17/10/2021 | Job posted, Job details, Search job, Part time job, Full time job, Remote job, Post job, Delete job, Edit CV, Create CV, Add to wishlist
2 | Debug | 17/10/2021
3 | Test | 17/10/2021
4 | Update database | 17/10/2021
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## Week 5+6
PROJECT REPORT
Group | Group 2
Week 1 | Iteration 2 (04/10/2021-17/10/2021)
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Post job | Completed
2 | Job details | Completed
3 | List Job posted | Completed
4 | Notification | Completed
5 | Approve Cv | Completed
6 | Create Cv | Completed
7 | View Cv | Completed
8 | Edit Cv | Completed
9 | Submit Cv | Completed
10 | View user profile | Completed
11 | Account management | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Post job | Nghia
2 | Job details | Loc
3 | List Job posted | Loc
4 | Notification | Loc
5 | Approve Cv | Kien
6 | Create Cv | Kien
7 | View Cv | Kien
8 | Edit Cv | Nghia
9 | Submit Cv | Kien
10 | View user profile | Nghia
11 | Account management | Loc
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | business logic | In Progress
2 | Tồn tại một số bug chưa xác định | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Test tất cả các use case | 31/10/2021
2 | Fix bug | 31/10/2021
3 | Code | 31/10/2021 | Account Management, Account Delete, Account Profile, Approve CV, List CV, View Wallet, Payment, Paging, Filter
4 | Test | 31/10/2021
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## Week 7+8
PROJECT REPORT
Group | Group 2
Week 7+8 | Iteration 3 (18/10/2021-31/10/2021)
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Forget Password | Completed
2 | RemoteJob | Completed
3 | Full-time Job | Completed
4 | Part-time Job | Completed
5 | Finance management | Completed
6 | Delete account | Completed
7 | view banner list | Completed
8 | Approve Banner | Completed
9 | Banner details | Completed
10 | View wallet | Completed
11 | submit banner | Completed
12 | View wishlist | Completed
13 | Add to wishlist | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Forget Password | Nghia
2 | RemoteJob | Thanh
3 | Full-time Job | Thanh
4 | Part-time Job | Thanh
5 | Finance management | Kien
6 | Delete account | Nghia
7 | view banner list | Loc
8 | Approve Banner | Loc
9 | Banner details | Loc
10 | View wallet | Nghia
11 | submit banner | Loc
12 | View wishlist | Kien
13 | Add to wishlist | Kien
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Tồn tại một số bugs | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Fix bug | 2021-11-12
2 | Test tất cả các use case | 2021-11-12
3 | Code | 2021-11-12 | Paging, Filter, Add money, Authorize Payment, Execute Payment, Review Payment
4 | hoàn thành tài liệu | 2021-11-12 | srs,backlog, design
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## Week 9+10
PROJECT REPORT
Group | Group 2
Week 7+8 | Iteration 3 (1/11/2021-12/11/2021)
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Paging | Completed
2 | Filter | Completed
3 | Add money | Completed
4 | Authorize Payment | Completed
5 | Execute Payment | Completed
6 | Review Payment | Completed
7 | hoàn thành tài liệu | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Paging | Loc
2 | Filter | Nghia
3 | Add money | Loc
4 | Authorize Payment | Nghia
5 | Execute Payment | Kien
6 | Review Payment | Kien
7 | hoàn thành tài liệu | all member | chủ yếu là Kiên làm
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | lỗi front end 1 số trang jsp chưa kịp sửa | Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes